## Sheet1
THEME 1: IMPROVED OUTCOMES FOR CLIENTS - 22-23
Objective: Increase presence in St. Joseph County to be able to serve a greater number of clients.
Action Steps | Person Responsible | Time Frame | Method for Measurement | Progress/Updates
Media/Social Media of services we offer, CCBHC etc. | Management | FY 23 | Number of posts via Facebook; increase in the number of followers per quarter, interactions (initial gains looking for 5% per quarter) | Q1 Update: Placed on hold due to the rebranding of the agency and the new website redesign. Q2 Update: Engaged in contract with Inspirational Studios to handle all Social Media Engagement. This is to start 5-1-23
THEME 1: IMPROVED OUTCOMES FOR CLIENTS - 22-23
Objective: To enhance services by providing a greater array of services to clients
Action Steps | Person Responsible | Time Frame | Method for Measurement | Progress/Updates
Zero Suicide Implementation | CCBHC Director and Zero Suicide Implementation Team | Ongoing | Operational goal of fully implemented be end of FY 23 | Q1 Update: Training is to occur on January 17 & 18th for AMSR and February 2-1 QPR training for non-clinical staff and then we will be implementing it fully across the agency after trainings occur. Q2 Update: Zero Suicide Workgroup developing clinical care pathways
EBP training for staff, offering EMDR and DBT to more clients | outpatient | ongoing | Number of staff trained at beginning of FY23 vs total number staff trained end of FY 23, number of EBPs being utilized each quarter in conjunction with staff trained | Q1 Update: Clients: TFCBT 1391, DBT 168, EMDR 2, MHHV 150, MOTINT 1158, Play Therapy 254, PMTO 7, TFCBT 32, TREM 1, IDDT 183. Q2 Update Staff: 6 DBT, 1 EMDR, 3 TF-CBT trained TCBT 1366, DBT 89 EMDR 5 MHHV 132, MOTINT 1201 PLAYTHERAPY 146 PMTO 8 TFCBT 40 IDDT 228
MAT (Medication Assisted Treatment) | CCBHC Director Medical Director and Nursing Staff | Ongoing | Seeing first clients in Q1. Fully up and running by Q2. Each quarter increase number of members by 7 till full at 30. | Q1 Update: Training and policies in place, first client openings are scheduled for the end of January. Q2 Update: we have had two clients sign up for the program. 1st client did not participate and no showed. 2nd client will need to be discharged from the program due to noncompliance to the program
THEME 1: IMPROVED OUTCOMES FOR CLIENTS - 22-23
Objective: To Encourage clients to be in the least restrictive settings possible.
Action Steps | Person Responsible | Time Frame | Method for Measurement | Progress/Updates
Include case managers in meetings regarding clients in specialized residential homes, while reviewing assessments to determine correct Level of Care for Clients | Director of UM | FY 23 | Number of clients currently in Specialized Residential each quarter with a number of clients successfully transitioned into a less restrictive setting | Q1 Update: October 99 clients in Spec Res, November 95 clients Q2 Update : December: 85 January: 85 February:83
Increase provider network capabilities with larger providers for CLS homes in our area as well as Specialized Residentials. | Director of Provider Network | FY 23 | Quarterly updates of additional providers added (initially looking for at least 1 a quarter but may be difficult due to staffing issues faced through St. Joseph County) | Q1 Update: 4 New Spec Res homes credentialed. Q2 Update:
THEME 2: INTEGRATED HEALTHCARE EXCELLENCE 22-23
Objective: To improve clients' physical health through education
Action Steps | Person Responsible | Time Frame | Method for Measurement | Progress/Updates
Increase client awareness of and utilization of dietitian | CCBHC Director | FY22-23 | Quarterly Reports of number of referrals to dietician and also of visits kept | Q1 Update: Dietitian referral form has been completed and will be rolled out to clinicians in Q2. Q2 Update: Volume continues to increase, employee rollout did not occur due to the dietician having personal issues that prevented her from taking on even more referrals. Q3 we are hoping to role out to clinians.
THEME 2: INTEGRATED HEALTHCARE EXCELLENCE 22-23
Objective: To improve clients' overall functioning through coordination with physical health providers
Action Steps | Person Responsible | Time Frame | Method for Measurement | Progress/Updates
Utilizing Nurse Care Coordinator(s) to meet local PCP and develop a point of contact/provide education | CCBHC Director | FY23 Q3 & 4 | Quarterly reports of number of PCP providers visited and monitor number of referrals from those PCP locations. | Q1 Update: Placed on hold due to the rebranding of the agency. Looking to start doing this once the rebrand has been completed. Q2 Update: Still on hold. Will pursue heavily in May when we roll out our new name.
Bi-yearly or Quarterly Meetings between Sturgis/Three Rivers Hospital and CMH | CEO and Director of UM | FY22-23 | 2-4 Meetings per year based on hospital desire and minutes of those meetings. | Q1 Update: Three Rivers just hired a new CEO, and will be meeting with Grae and myself to see how we can help each other. Sturgis Hospital has stated that they are currently working well together and will need to revisit if that changes. Q2 Update: Met with Three Rivers CEO. Things are going well, still have concerns on wait times for admission and lack of beds from both hospitals, but this is a statewide issue and no clear way to solve at this time.
THEME 3: EMPLOYEE ENGAGEMENT AND RETENTION 22-23
Objective: To recruit and retain staff at St. Joe CMH & SAS
Action Steps | Person Responsible | Time Frame | Method for Measurement | Progress/Updates
Monitor salaries and benefits to ensure we are comparable if not the leader in the region for clinical staff in order to retain the professional staff that we have acquired and entice new staff needed. | CEO, CFO, HR | Ongoing | Comparison of CMH Salary Survey with current wages with report to board once new survey has been received. Adjustments made as necessary based on new survey | Q1 Update: Presented at 1/31/23 Board meeting the comparison to the 2021 survey results. This should be presented back to the board when the 2022 results are available. Q2 Update: 2022 Survey Results have not been sent or received yet. I did apply for an ARPA Grant for 3 years to be able to provide additional supports for staff retention. We were approved for this grant. This can allow for longevity payments, increase in salaries, and recruitment bonus'.
Continue to participate and expand into more loan repayment programs for all departments wherever offered and possible. | CEO, Supervisory staff and HR | Ongoing | HRSA enrollment. CMH & SAS becomes a certified HRSA site. | Q1 Update: Waiting for the HRSA grant application window to reopen so that we can add student loan forgiveness. Q2 Update: Site Applications are not yet available. Still waiting for the window so that I can apply for our organization.
Create onboarding system for new staff | Management | Ongoing | Onboarding policy, training guide created | Q1 Update: Management and new employees have met to create an upgraded onboarding system. Our first employee to use the system will be January 9th. Q2 Update: We have had a few new employees go through our new program, it seems to have better flow. Still seems to be a lot of information all at once, but not sure how to fix that at this point. We are working on a 'handbook' of sorts to be able to be a reference guide to give in addition to our new hire onboarding.
Encourage employee interest and participation in employee morale and wellness activities. | ERWC | Ongoing | Increased number ERWC members, attendance at each event put on by ERWC. | Q1 Update: Company dinner was well attended. Added an additional 6 ERWC members for new ideas and suggestions. Q2 Update: ERWC continues to provide events each month to be able to have staff interact at all three locations and seem to be gaining traction in attendance.
Clinical Directors will participate in Components for Enhancing Career Experience and Reducing Trauma (CE-CERT) and implement within the agency | Clinical Supervisors | Ongoing | CE-CERT implementation | Q1 Update: Management is currently attending CE-CERT training. Currently attended 3 out of 10 trainings and a 4 hour introductions. Q2 Update: Training is complete, consultation calls are ongoing. Travis and Kathleen are the only remaining clinical directors participating.
THEME 4: COMMUNITY ENGAGEMENT 22-23
Objective: To collaborate interagency cooperativeness both in the community and at our main location
Action Steps | Person Responsible | Time Frame | Method for Measurement | Progress/Updates
Create satellite facilities in both Sturgis and Three Rivers, our two most heavily populated areas in St. Joseph County. | CEO SUD/Outpatient Directors | 1st half of FY 22-23 | Physical opening of two locations with full staff and seeing clients. | Q1 Update: Sturgis Location opened December 1st 2022, Three Rivers location opened January 3rd 2023. Q2 Update: New Co-Occurring Therapist for Sturgis Location. Hired New Access Clinician for Three Rivers location to help with Influx of DRC clients needing intakes, as well as being able to offer walk in intakes in the future.
Add Mobile Crisis - Police Liaisons to both Three Rivers This should Mirror Sturgis Police Department | CEO UM/Emergency Services Director | 1st half of FY 22-23 | adding additional position. Show number of calls pre/post addition of staff member. | Q1 Update Position has been posted. No current applications. Will continue to post and look for qualified applicants. Q2 Update: We had an interested Candidate, interviewed well, but when offered the job, it was decided that he shouldn't switch jobs prior to having a new child so he declined to opening. No other candidates have applied at this time.
THEME 5: FINANCIAL SOLVENCY 22-23
Objective: To continue to remain fiscally responsible and utilize
Action Steps | Person Responsible | Time Frame | Method for Measurement | Progress/Updates
Reconciliation of CCBHC | CFO, Financial Controller, CEO | FY 23 | Follow state Reconciliation templates and complete reconciliation | Q1 Update: State Guidelines have still not be finalized. Audits have been in progress, but we still do not have a final reconciliation template. Q2 Update: Reconciliation has been completed, all forms have been turn into the state per guidelines. No response yet from the state on acceptance or not.
Utilization Management of high utilizers of resources and funding sources | CFO, Financial Controller, UM | ongoing | Monthly Meetings to determine appropriate usage of resources and identifying alternative options if available | Q1 Update: Ongoing meetings monthly to review. Q2 Update:
Monitor Internal controls | CFO, Financial Controller | ongoing | Clean financial Audits | Q1 Update: Current Financial audit is ongoing. To our knowledge at this point in time, there are no findings. April the auditors will present to the Board as a whole. Q2 Update:

## Sheet2
THEME 1: OPERATIONAL EXCELLENCE
THEME 2: INTEGRATED HEALTHCARE EXCELLENCE
THEME 3: COMMUNITY ENGAGEMENT
THEME 4: CULTURE CHANGE